Minutes of the meeting of the Services and Environment Committee held on 18th February 2026 at 19:00hrs in the Council Chamber at Shefford House, 15 High Street, Shefford, SG17 5DD or viewed using www.zoom.us

Present: , Cllr Fred Wilson (Chair), Cllr Nicola King, Cllr Christine Culleton, Cllr Steve Nash and Cllr Sue Silver.

Via Zoom: Cllrs Mark Greenwood

Town Clerk:	T Medley C Quinlan (Admin Assistant)

- Apologies Cllrs Elsa Tattersfield, Paul Mackin and Danny Cummins.

- Declarations of interest: None

- Public Question Time:

- Minutes

The minutes of the meeting of the committee on 14th January 2026 were reviewed, proposed by Cllr Culleton, seconded by Nash and agreed as a true record by all.

- UK Prosperity

Cllrs discussed the project for the noticeboard outside the fire station; it was agreed that the Notus double door external noticeboard would be ordered. The stone planter will also be ordered. Installation will be arranged with a CBC approved contractor.

The CCTV for The Bridge was discussed. CQ has approached The Wells and Co Brewery for permission to have the CCTV on the outside of their building. She will chase them to see if she can establish a timescale for them granting permission, TM expressed concerns for the project in terms of it being completed by end of financial year. TM has invoiced CBC to release the funding, but it cannot be released until permission has been granted, if permission is not granted before the end of the financial year the TC will potentially loose the funding. TM will list it on the full council agenda, CQ will be able to provide an update.

- Shefford Fun Day 2026

Fund day has been agreed for 20th June 2026. Amer has been booked for amusement, and a resident is taking a lead on arranging the stalls and entertainment.

Cllr Nash proposed payments:

Amer £1000 deposit

Community organiser £300 to organise the event.

Set up tech costs £300.

Seconded by Cllr Culleton, all agreed.

The Fun day is earlier than usual and other events are running in the Town, but the organiser will persevere with organising the event.

Eat Feast have been arranged.

The compere needs to be agreed, it was suggested Ken may be available, Cllr Nash also agreed.

- Santa’s grotto:

Amer has been booked for Friday 11th December 2026 for the Santa’s grotto in the Town centre, same plan as previously, the same Santa has also been booked.

- Green Flag awards:

The application has been submitted, CQ will complete the charity return and confirm with the Green Flag organisers that it has been completed.

- Play Inspections for 2026:

Cllr agreed for Clerks to book the Annual play inspections for May 2026, CQ will confirm the booking. Once the inspections have been carried out Cllrs will commence carrying out weekly inspections with CPM carrying out one inspection per month, TM will confirm with CPM.

Lucas Way Play area needs to be jet washed, CQ has received a quote for £495.00. proposed by Cllr Wilson, seconded by Cllr Culleton, all agreed.

- CBC Tree funding:

Cllrs discussed the CBC tree project and the Oak tree project being run by CPRE as part of their 40 yr celebrations. CQ and TM will contact the P3 group to discuss further.

- Bench seat at Southbridge way:

TM will follow this up.

Meeting closed 19:48hrs.